## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a developer, I want the FastAPI backend and React frontend project structure set up so that I have a working foundation to build the multi-agent system on. | Must Have | None | J Rakshitha | Completed
Sprint 1 | Sprint 1 | US002 | As a system, I want a Coordinator Agent and core database models so that all specialized agents can be orchestrated centrally. | Must Have | US001 | J Rakshitha | Completed
Sprint 1 | Sprint 1 | US003 | As a developer, I want LangChain configured with the Gemini LLM so that reasoning agents can generate intelligent responses. | Must Have | US001 | J Rakshitha | Completed
Sprint 1 | Sprint 1 | US004 | As a system, I want a Hybrid AI Client (LLM + rule-based fallback) so that the platform keeps working even if the LLM API is unavailable. | Must Have | US003 | J Rakshitha | Completed
Sprint 1 | Sprint 1 | US005 | As a developer, I want LangChain Prompt Templates for every reasoning agent so that prompts are structured, centralized and easy to maintain. | Should Have | US003 | J Rakshitha | Completed
Sprint 1 | Sprint 1 | US006 | As a QA engineer, I want an automated pytest test suite so that I can verify system correctness without manual re-testing every time. | Should Have | US002 | J Rakshitha | Completed
Sprint 1 | Sprint 1 | US007 | As a developer, I want Dev-Collaboration agents (Code-Watch, Overlap Detection, Conflict Prediction, Resolution Suggestion) so that merge conflicts are predicted and resolved before they happen. | Must Have | US002 | J Rakshitha | Completed
Sprint 1 | Sprint 1 | US008 | As a developer, I want AIOps agents (Monitoring, Root-Cause, Severity, Remediation, Escalation) so that production incidents are detected and auto-resolved end-to-end. | Must Have | US002 | J Rakshitha | Completed
Sprint 1 | Sprint 1 | US009 | As a user, I want a React dashboard with dark/light mode and live tabs so that I can visually monitor both modules of the engine. | Must Have | US001 | J Rakshitha | Completed
Sprint 1 | Sprint 1 | US010 | As a user, I want real-time WebSocket updates so that the dashboard reflects agent activity instantly without a manual refresh. | Should Have | US009 | J Rakshitha | Completed
Sprint 1 | Sprint 1 | US011 | As a system, I want the Coordinator Agent to link production incidents to risky recent commits so that root-cause analysis accounts for recent code changes. | Should Have | US007, US008 | J Rakshitha | Completed
Sprint 1 | Sprint 1 | US012 | As a system, I want short-term and long-term memory (a Knowledge Base) so that agents reuse past insights instead of re-reasoning from scratch every time. | Should Have | US004 | J Rakshitha | Completed
Sprint 1 | Sprint 1 | US013 | As a system, I want a real External Lookup Agent using GitHub's public Issue Search API so that incidents are cross-referenced against genuine external data sources. | Could Have | US008 | J Rakshitha | Completed
Sprint 2 | Sprint 2 | US014 | As a system, I want a Tool Registry of custom enterprise tools/API connectors so that agents have one uniform catalog of invocable actions. | Must Have | US013 | J Rakshitha | Completed
Sprint 2 | Sprint 2 | US015 | As a system, I want a Tool Selector Agent with intelligent (LLM + rule-based) selection so that the best tool is chosen automatically for a given situation. | Must Have | US014 | J Rakshitha | Completed
Sprint 2 | Sprint 2 | US016 | As a system, I want a Tool Executor Agent with exception handling so that a failing tool call can never crash the pipeline or a live demo. | Must Have | US015 | J Rakshitha | Completed
Sprint 2 | Sprint 2 | US017 | As a QA engineer, I want automated tests for tool invocation and exception handling so that the tool-selection logic is verifiably correct. | Must Have | US016 | J Rakshitha | Completed
Sprint 2 | Sprint 2 | US018 | As a system, I want tool executions tracked and an accuracy endpoint exposed so that action execution accuracy can be validated with real measured data. | Must Have | US016 | J Rakshitha | Completed
Sprint 2 | Sprint 2 | US019 | As a user, I want a Tool Integration panel in the dashboard so that I can see available tools and try intelligent tool selection live. | Should Have | US018 | J Rakshitha | Completed
Sprint 2 | Sprint 2 | US020 | As a developer, I want the intelligent Tool Selector wired into the real incident pipeline (not just a standalone demo) so that remediation decisions are genuinely tool-driven. | Must Have | US015, US008 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US021 | As a system, I want a Notification Agent delivering multi-channel team alerts (WebSocket, Gmail SMTP, Slack, Discord) so that conflicts and incidents reach the team instantly. | Must Have | US020 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US022 | As a user, I want a Team Notifications panel on the Overview page so that I can audit all alert deliveries across channels. | Must Have | US021 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US023 | As a user, I want Code Review Agent output visible on conflict cards so that merge-risk advice is actionable in the UI. | Must Have | US007 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US024 | As a system, I want full agent decision logging across Dev-Collab and AIOps pipelines so that every step is explainable. | Must Have | US011 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US025 | As a QA engineer, I want Milestone 3 coordination and memory tests so that cross-module linking and knowledge base behaviour are verified. | Must Have | US024 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US026 | As a system, I want a GitHub webhook endpoint for real-time PR events so that conflicts sync without manual button clicks. | Must Have | US013 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US027 | As a system, I want Alembic DB migrations with SLA fields on incidents so that schema updates do not require deleting the database. | Must Have | US008 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US028 | As a user, I want a live SLA countdown timer on AIOps incident cards so that SLA compliance is visible during demos. | Should Have | US027 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US029 | As a developer, I want the Hybrid AI Client migrated to the google-genai SDK so that AQ and AIza Gemini keys both work. | Must Have | US004 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US030 | As a QA engineer, I want enterprise integration tests (webhook, Slack, Discord, Gmail, SLA) so that external channels are regression-safe. | Must Have | US021, US026 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US031 | As a developer, I want a shared GitHub sync service used by manual sync and webhooks so that conflict detection logic is not duplicated. | Must Have | US026 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US032 | As a developer, I want README and .env.example updated for Milestone 3 enterprise features so that the project is submission-ready. | Should Have | US030 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US033 | As a system, I want a Repository Discovery Agent performing real AST scans so that code symbols and complexity are indexed for conflict analysis. | Must Have | US013 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US034 | As a system, I want a Semantic Analysis Agent combining AST diff with Hybrid AI so that logic-level merge risks are explained. | Must Have | US033 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US035 | As a system, I want a Resolution Synthesizer Agent scoring three merge strategies so that the best coordination option is selected. | Must Have | US007 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US036 | As a system, I want a Quality Agent producing A/B/C grade scorecards from cyclomatic complexity metrics. | Must Have | US033 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US037 | As a system, I want semantic RAG search over the knowledge base using Gemini embeddings so that past patterns are retrieved by meaning. | Must Have | US011 | J Rakshitha | Completed
Sprint 3 | Sprint 3 | US038 | As a developer, I want README, pytest config, and milestone documents updated for enterprise features so that submission is complete. | Should Have | US037 | J Rakshitha | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 206 | 8 | 10 | 9 | 12 | 14 | 15 | 8.6 | 4.2 | 2.8 | 1.4 | 5 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T001 | Set up backend FastAPI project structure, folders and requirements.txt | 2026-06-29 | 2026-06-29 | J Rakshitha | Setup | Completed | 3 | Day 1: 0
US001 | T002 | Set up frontend React + Vite + Tailwind project structure | 2026-06-29 | 2026-06-30 | J Rakshitha | Setup | Completed | 4 | Day 1: 4; Day 2: 0
US002 | T003 | Design and implement Coordinator Agent and core DB models (dev_collab, incident) | 2026-06-30 | 2026-07-01 | J Rakshitha | Development | Completed | 5 | Day 2: 5; Day 3: 0
US003 | T004 | Configure LangChain with Gemini (ChatGoogleGenerativeAI) integration | 2026-07-01 | 2026-07-01 | J Rakshitha | Development | Completed | 3 | Day 3: 0
US004 | T005 | Build Hybrid AI Client with rule-based fallback logic | 2026-07-01 | 2026-07-02 | J Rakshitha | Development | Completed | 4 | Day 3: 4; Day 4: 0
US007 | T006 | Implement Dev-Collaboration agents: Code-Watch, Overlap Detection, Conflict Prediction, Resolution Suggestion | 2026-07-02 | 2026-07-04 | J Rakshitha | Development | Completed | 8 | Day 4: 8; Day 5: 4; Day 6: 0
US008 | T007 | Implement AIOps agents: Monitoring, Root-Cause, Severity, Remediation, Escalation | 2026-07-03 | 2026-07-05 | J Rakshitha | Development | Completed | 8 | Day 5: 8; Day 6: 4; Day 7: 0
US009 | T008 | Build React dashboard UI (Overview, Dev-Collaboration, Incident Response pages, dark/light theme) | 2026-07-04 | 2026-07-09 | J Rakshitha | Development | Completed | 7 | Day 6: 7; Day 7: 5.6; Day 8: 4.2; Day 9: 2.8; Day 10: 1.4; Day 11: 0
US010 | T009 | Implement WebSocket real-time updates (backend broadcast + frontend live socket context) | 2026-07-04 | 2026-07-04 | J Rakshitha | Development | Completed | 3 | Day 6: 0
US011 | T010 | Implement cross-module linking (Coordinator Agent commit-to-incident linking) | 2026-07-05 | 2026-07-05 | J Rakshitha | Development | Completed | 3 | Day 7: 0
US012 | T011 | Implement Memory Agent (short-term recent-decision context + long-term Knowledge Base) | 2026-07-08 | 2026-07-08 | J Rakshitha | Development | Completed | 4 | Day 10: 0
US013 | T012 | Implement External Lookup Agent using GitHub's public Issue Search API | 2026-07-09 | 2026-07-09 | J Rakshitha | Development | Completed | 3 | Day 11: 0
US006 | T013 | Write pytest test suite (14 tests) covering Dev-Collaboration, AIOps, Memory and System endpoints | 2026-07-09 | 2026-07-10 | J Rakshitha | Testing | Completed | 5 | Day 11: 5; Day 12: 0
US005 | T014 | Refactor raw-string prompts into LangChain ChatPromptTemplate to align with Milestone 1 brief | 2026-07-10 | 2026-07-10 | J Rakshitha | Development | Completed | 2 | Day 12: 0
SPRINT 2 BACKLOG
US014 | T015 | Design and implement Tool Registry (Tool dataclass + registration for 5 connectors) | 2026-07-13 | 2026-07-14 | J Rakshitha | Development | Completed | 4 | Day 1: 4; Day 2: 0
US014 | T016 | Implement Tool Handlers: GitHub lookup, escalation ticket, knowledge-base query, restart-service, clear-cache | 2026-07-14 | 2026-07-15 | J Rakshitha | Development | Completed | 5 | Day 2: 5; Day 3: 0
US015 | T017 | Implement Tool Selector Agent (LLM selection + keyword-based rule fallback) with LangChain prompt template | 2026-07-15 | 2026-07-16 | J Rakshitha | Development | Completed | 5 | Day 3: 5; Day 4: 0
US016 | T018 | Implement Tool Executor Agent with try/except safety net and ToolExecutionLog model | 2026-07-16 | 2026-07-17 | J Rakshitha | Development | Completed | 4 | Day 4: 4; Day 5: 0
US020 | T019 | Wire Tool Selector/Executor into the real AIOps incident pipeline, replacing the hardcoded remediation rule | 2026-07-17 | 2026-07-17 | J Rakshitha | Integration | Completed | 3 | Day 5: 0
US018 | T020 | Implement /api/tools/accuracy endpoint (overall + per-tool measured success rate) | 2026-07-17 | 2026-07-18 | J Rakshitha | Development | Completed | 2 | Day 5: 2; Day 6: 0
US019 | T021 | Build Tool Integration frontend panel (tool chips, try-selection UI, accuracy display) | 2026-07-18 | 2026-07-18 | J Rakshitha | Development | Completed | 4 | Day 6: 0
US017 | T022 | Write automated tests for tool selection, invocation, exception handling and accuracy (7 tests) | 2026-07-18 | 2026-07-19 | J Rakshitha | Testing | Completed | 4 | Day 6: 4; Day 7: 0
US017 | T023 | Regression-test full suite (21 tests) after Milestone 2 integration and fix issues found | 2026-07-19 | 2026-07-20 | J Rakshitha | Testing | Completed | 3 | Day 7: 3; Day 8: 0
US020 | T024 | Update README with Milestone 2 alignment mapping and push to GitHub | 2026-07-20 | 2026-07-20 | J Rakshitha | Documentation | Completed | 2 | Day 8: 0
SPRINT 3 BACKLOG
US021 | T025 | Implement Notification Agent multi-channel delivery (Slack incoming webhook) | 2026-07-27 | 2026-07-28 | J Rakshitha | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US021 | T026 | Add Discord webhook channel + Gmail SMTP configurable team recipients | 2026-07-28 | 2026-07-29 | J Rakshitha | Development | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US022 | T027 | Build Team Notifications panel component on Overview page | 2026-07-29 | 2026-07-30 | J Rakshitha | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US023 | T028 | Display Code Review Agent notes on Dev-Collab conflict cards | 2026-07-30 | 2026-07-31 | J Rakshitha | Development | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US024 | T029 | Expand incident pipeline decision logging for all agents (Severity, Tool, Notification) | 2026-07-31 | 2026-08-01 | J Rakshitha | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US026 | T030 | Implement GitHub webhook route with HMAC signature verification | 2026-08-01 | 2026-08-02 | J Rakshitha | Development | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US031 | T031 | Extract shared github_sync_service for manual sync and webhook triggers | 2026-08-02 | 2026-08-02 | J Rakshitha | Integration | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US027 | T032 | Set up Alembic migrations and add SLA fields (sla_minutes, sla_deadline, escalated_to) | 2026-08-02 | 2026-08-03 | J Rakshitha | Development | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US028 | T033 | Build SlaCountdown live timer component on AIOps incident cards | 2026-08-03 | 2026-08-03 | J Rakshitha | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US029 | T034 | Migrate Hybrid AI Client from LangChain to google-genai SDK (AQ + AIza keys) | 2026-08-03 | 2026-08-04 | J Rakshitha | Development | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US030 | T035 | Add GET /api/system/integrations and test endpoints (email, Discord, Teams) | 2026-08-04 | 2026-08-04 | J Rakshitha | Development | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US025 | T036 | Write Milestone 3 tests: cross-module linking, memory, notifications, code review | 2026-08-04 | 2026-08-04 | J Rakshitha | Testing | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US030 | T037 | Write enterprise integration tests (webhook, Slack, Discord, Gmail, SLA) — 14 tests | 2026-08-04 | 2026-08-04 | J Rakshitha | Testing | Completed | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US029 | T038 | Write LLM hybrid tests for google-genai SDK fallback behaviour — 3 tests | 2026-08-04 | 2026-08-04 | J Rakshitha | Testing | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US032 | T039 | Fix Simulate Conflict/Incident frontend timeout (45s) and clearer error messages | 2026-08-04 | 2026-08-04 | J Rakshitha | Development | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US026 | T040 | Configure ngrok + GitHub webhook secret sync; verify live PR delivery | 2026-08-04 | 2026-08-04 | J Rakshitha | Integration | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US032 | T041 | Update README, .env.example with M3 features; full regression (46+ tests) | 2026-08-04 | 2026-08-04 | J Rakshitha | Documentation | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US033 | T042 | Implement Repository Discovery Agent + code_parser AST service + CodeSymbol model | 2026-07-27 | 2026-07-28 | J Rakshitha | Development | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US034 | T043 | Implement Semantic Analysis Agent with AST diff + Hybrid AI prompts | 2026-07-28 | 2026-07-29 | J Rakshitha | Development | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US035 | T044 | Implement Resolution Synthesizer Agent with three scored strategies | 2026-07-29 | 2026-07-30 | J Rakshitha | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US036 | T045 | Implement Quality Agent + evaluate_code_quality tool with A/B/C grading | 2026-07-30 | 2026-07-31 | J Rakshitha | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US037 | T046 | Implement Knowledge Search RAG + embedding service + semantic_knowledge_search tool | 2026-07-31 | 2026-08-01 | J Rakshitha | Development | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US033 | T047 | Wire enterprise pipeline: Discovery → Semantic → Quality → Code Review → Notify | 2026-08-01 | 2026-08-02 | J Rakshitha | Integration | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US037 | T048 | Add Alembic migration 002_enterprise_intelligence + extend ConflictEvent JSON fields | 2026-08-02 | 2026-08-03 | J Rakshitha | Development | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US037 | T049 | Update DevCollab UI + Knowledge Base semantic search panel for enterprise outputs | 2026-08-03 | 2026-08-04 | J Rakshitha | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US038 | T050 | Write test_enterprise_phase5.py (6 tests) + root pytest.ini; full suite 55 passed | 2026-08-04 | 2026-08-04 | J Rakshitha | Testing | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US038 | T051 | Update README, milestone Excel docs, git commit and push to GitHub | 2026-08-04 | 2026-08-04 | J Rakshitha | Documentation | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 6 | Windows PowerShell could not activate the Python virtual environment using the Linux/Mac 'source' command. | Identified PowerShell requires 'venv\Scripts\Activate.ps1' instead of 'source venv/bin/activate'; documented the correct Windows command.
Sprint 1 | Day 6 | 'pip install' failed while building pydantic-core from source — no prebuilt wheel for Python 3.13 on Windows, and the Rust/MSVC linker was missing. | Removed strict '==' version pins from requirements.txt and switched to flexible '>=' minimum versions compatible with the already-installed newer packages.
Sprint 1 | Day 7 | Backend returned HTTP 500 Internal Server Error when creating an incident via /api/incidents/ingest-metrics. | Diagnosed a missing SQLAlchemy back_populates relationship on the RemediationAction model; added the missing 'incident' relationship attribute.
Sprint 1 | Day 7 | Frontend dashboard showed 'Backend not reachable' even though the FastAPI server was running. | Root-caused as a CORS mismatch (Vite auto-selected port 5174 instead of 5173); updated CORS middleware to allow any localhost port via allow_origin_regex.
Sprint 1 | Day 9 | Dark/Light theme toggle changed internal state but the UI colors never visually changed. | Found that light-theme CSS variables were never defined; implemented CSS custom properties for both themes and mapped Tailwind color tokens to them.
Sprint 2 | Day 6 | 'pytest' command was not recognized in a new terminal session. | Root-caused as the virtual environment not being activated in that terminal; re-ran 'venv\Scripts\Activate.ps1' before invoking pytest.
Sprint 2 | Day 8 | 'git push' was rejected with 'failed to push some refs... fetch first' on the very first push to the new GitHub repository. | Used 'git push --force' for this initial push, since the remote only contained auto-generated placeholder content, not history that needed preserving.
Sprint 3 | Day 3 | POST /api/incidents/ returned HTTP 500 — SQLite DB missing new SLA columns after model update. | Ran 'alembic upgrade head' to apply migration 001_add_incident_sla_fields without deleting existing data.
Sprint 3 | Day 5 | GitHub webhook deliveries returned HTTP 401 — signature mismatch between GitHub secret and backend .env. | Synced GITHUB_WEBHOOK_SECRET via GitHub API PATCH and verified signed ping returns 200 through ngrok.
Sprint 3 | Day 7 | Simulate Conflict button showed 'Backend not reachable' although FastAPI was running on port 8000. | Root cause was axios 10s timeout; LLM + Slack/Discord/Gmail pipeline takes 15-20s. Increased timeout to 45s in apiClient.js.
Sprint 3 | Day 9 | Microsoft Teams webhook setup failed — personal Gmail Microsoft account rejected by Power Automate (AADSTS500200). | Documented Teams as optional (M365 only); completed Slack + Discord + Gmail as live multi-channel demo instead.
Sprint 3 | Day 8 | Conflict list API crashed after adding enterprise columns — SQLite missing discovery_context. | Ran 'alembic upgrade head' for migration 002_enterprise_intelligence.
Sprint 3 | Day 9 | pytest from project root showed 48 async failures — backend/pytest.ini not loaded. | Added root pytest.ini with asyncio_mode=auto and testpaths=backend/tests.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-06-29 | 2026-07-12 | J Rakshitha | Writing an automated pytest test alongside every new agent, instead of relying only on manual UI testing. | Pinning exact dependency versions in requirements.txt — it caused Windows build failures; switched to flexible minimum-version pins. | The Hybrid AI design pattern (LLM + rule-based fallback) for every reasoning agent, and verifying each feature with a live screenshot before moving on. | Adopted a phase-wise build process (setup, core module, second module, cross-module linking, polish) with a syntax check after every phase to catch errors early.
2 | Sprint 2 | 2026-07-13 | 2026-07-26 | J Rakshitha | Checking new work against the official milestone brief line-by-line before coding, to avoid rework after the fact. | Assuming a feature was 'good enough' without doing an explicit gap-analysis against the stated requirements. | Wrapping every new external/tool call in try/except so a single failure can never break the live demo. | Added a dedicated Tool Registry + Selector + Executor layer with a matching automated test file, wired into the real incident pipeline rather than left as a standalone demo.
3 | Sprint 3 | 2026-07-27 | 2026-08-04 | J Rakshitha | Testing external integrations (Slack, Discord, Gmail, GitHub webhook) early with dedicated /api/system/test-* endpoints before UI demo. | Assuming 10s frontend timeout is enough when agents run LLM + three notification channels sequentially. | Multi-channel Notification Agent pattern — one simulate action alerts Slack, Discord, Gmail and dashboard in parallel. | Delivered enterprise 5-phase intelligence (Discovery, Semantic, Synthesizer, Quality, RAG) with 55 automated tests and live multi-channel demo.
4
5
6
7