## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | J Rakshitha | 2026-07-04 | 'pip install -r requirements.txt' failed while trying to compile pydantic-core from source (Rust/MSVC linker error) on Windows with Python 3.13. | Sprint 1 | J Rakshitha | Others | requirements.txt pinned an old exact pydantic version with no prebuilt wheel for Python 3.13. Removed strict '==' pins in favor of flexible '>=' minimum versions, letting pip resolve to an already-compatible newer build. | 2026-07-04 | Closed | Verified clean install completes without any compilation step.
2 | J Rakshitha | 2026-07-04 | StatCard component's accent color classes were built via Tailwind class-name string interpolation (e.g. bg-accent-${accent}), which Tailwind's static class scanner cannot detect, so the intended colors would have silently never rendered. | Sprint 1 | J Rakshitha | User Interface | Replaced the interpolated class names with a literal, fully-spelled-out class map so Tailwind's scanner can detect every class at build time. | 2026-07-04 | Closed | Self-caught during code review, before it ever reached the live demo.
3 | J Rakshitha | 2026-07-04 | POST /api/incidents/ingest-metrics returned HTTP 500 Internal Server Error when creating a new incident record. | Sprint 1 | J Rakshitha | Logical | Found a missing SQLAlchemy back_populates relationship: RemediationAction had no 'incident' attribute matching Incident.actions. Added the missing relationship() to fix the ORM mapper configuration. | 2026-07-04 | Closed | Confirmed fixed after backend restart; incident creation now returns HTTP 200.
4 | J Rakshitha | 2026-07-04 | Frontend dashboard displayed 'Backend not reachable' on every page even though the FastAPI server was confirmed running. | Sprint 1 | J Rakshitha | Others | Root cause was a CORS origin mismatch: Vite had auto-selected port 5174 (5173 was already in use) but the backend only allowed 5173. Updated CORSMiddleware to accept any localhost/127.0.0.1 port via allow_origin_regex. | 2026-07-04 | Closed | Verified live data loading correctly on Overview, Dev-Collaboration and Incident Response tabs.
5 | J Rakshitha | 2026-07-05 | Dark/Light theme toggle button changed internal state on click but produced no visible change in the UI colors. | Sprint 1 | J Rakshitha | User Interface | Light-theme color values were never defined; only a dark palette existed. Implemented CSS custom properties for both themes (:root for dark, html.light overrides) and mapped every Tailwind color token to them. | 2026-07-05 | Closed | Confirmed both themes render correctly across all pages after fix.
6 | J Rakshitha | 2026-07-18 | The Tool Selector's rule-based fallback can tie-break toward 'create_escalation_ticket' instead of a more specific tool (e.g. restart_service) when the situation text happens to contain a severity keyword like 'P1' alongside a remediation keyword, because the first-registered tool wins ties. | Sprint 2 | J Rakshitha | Logical | Not yet fixed — logged for future refinement of the tie-breaking rule (e.g. weight keyword specificity instead of first-match-wins). |  | Open | Non-blocking: the selected tool is still a valid, explainable choice; no incorrect or crashing behavior. Low priority.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others